## Timeline
GANTT CHART
PROJECT TITLE |  | AI based Smart Attendance System
PROJECT GUIDE |  | Prof. Anagha Aher |  |  | DATE | 2020-07-21
PROJECT CO.GUIDE |  | Prof. Neha Deshmukh
INSTUTUTE & DEPARTMENT NAME |  | A.P. Shah Institute Of Technology
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [34 empty] | PHASE TWO | [41 empty] | PHASE THREE | [106 empty] | PHASE FOUR | [25 empty] | PHASE FIVE
[7 empty] | WEEK1 | [6 empty] | WEEK2 | [6 empty] | WEEK3 | [6 empty] | WEEK4 | [6 empty] | WEEK5 | [6 empty] | WEEK6 | [6 empty] | WEEK7 | [6 empty] | WEEK8 | [6 empty] | WEEK9 | [6 empty] | WEEK10 | [6 empty] | WEEK11 | [6 empty] | WEEK12 | [6 empty] | WEEK13 | [6 empty] | WEEK14 | [6 empty] | WEEK15 | [6 empty] | WEEK16 | [6 empty] | WEEK17 | [6 empty] | WEEK18 | [6 empty] | WEEK19 | [6 empty] | WEEK20 | [6 empty] | WEEK21 | [6 empty] | WEEK22 | [6 empty] | WEEK23 | [6 empty] | WEEK24 | [6 empty] | WEEK25 | [6 empty] | WEEK26 | [6 empty] | WEEK21 | [6 empty] | WEEK22 | [6 empty] | WEEK23 | [6 empty] | WEEK24 | [6 empty] | WEEK25
 | time axis 2020-07-21 to 2021-02-22
[224 empty] | S | S | S | time axis 2020-07-21 to 2021-02-22
1 | Project Conception and Initiation
1.1 | Research paper Search | Tejas,Jayesh,Yash | 2020-07-21 | 2020-08-10 | 3 | 100%
1.1.1 | Research paper finalization | Tejas,Jayesh,Yash | 2020-07-21 | 2020-08-10 | 3 | 100%
1.2 | Project Title | Tejas,Jayesh,Yash | 2020-07-21 | 2020-08-10 | 3 | 100%
1.3 | Abstract | Yash | 2020-08-11 | 2020-08-17 | 1 | 100%
1.4 | Objectives | Tejas,Jayesh,Yash | 2020-08-11 | 2020-08-24 | 2 | 100%
1.5 | Literature Review | Tejas | 2020-08-18 | 2020-08-24 | 1 | 100%
1.6 | Problem Definition | Tejas,Yash | 2020-08-18 | 2020-08-24 | 1 | 100%
1.7 | Scope | Jayesh,Yash | 2020-08-18 | 2020-08-24 | 1 | 100%
1.8 | Technology stack | Tejas,Jayesh,Yash | 2020-08-11 | 2020-08-24 | 2 | 100%
1.9 | Benefits for environment | Tejas | 2020-08-18 | 2020-08-24 | 1 | 100%
1.1 | Benefits for society | Jayesh | 2020-08-18 | 2020-08-24 | 1 | 100%
1.11 | Applications | Yash | 2020-08-18 | 2020-08-24 | 1 | 100%
2 | Project Design
2.1 | Proposed System | Tejas | 2020-08-25 | 2020-08-31 | 1 | 100%
2.2 | Design(Flow Of Modules) | Tejas,Jayesh | 2020-09-01 | 2020-09-07 | 1 | 100%
2.3 | Activity Diagram | Jayesh,Yash | 2020-09-01 | 2020-09-07 | 1 | 100%
2.4 | Use Case Diagram | Jayesh,Yash | 2020-09-02 | 2020-09-08 | 1 | 100%
2.5 | Description Of Use Case | Tejas | 2020-09-03 | 2020-09-09 | 1 | 100%
2.6 | Objectives | Tejas,Jayesh,Yash |  |  |  | 100%
2.7 | Objective-1 | Tejas | 2020-09-10 | 2020-09-24 | 2 | 100%
2.8 | Objective-2 | Jayesh | 2020-09-11 | 2020-09-25 | 2 | 100%
2.9 | Objective-3 | Jayesh,Yash | 2020-09-12 | 2020-09-26 | 2 | 100%
2.1 | Objective-4 | Yash | 2020-09-13 | 2020-09-27 | 2 | 100%
2.11 | Preparation Of Report | Tejas,Jayesh,Yash | 2020-09-27 | 2020-10-03 | 1 | 100%
3 | Project Implementation
3.1 | Objective-1 | Tejas | 2020-10-06 | 2020-10-24 | 3 | 80%
3.2 | Objective-2 | Jayesh | 2020-10-10 | 2020-10-26 | 3 | 80%
3.3 | Objective-3 | Jayesh,Yash | 2020-11-01 | 2020-11-21 | 3 | 80%
3.4 | Objective-4 | Yash | 2020-11-22 | 2020-12-07 | 3 | 80%
4 | Testing
4.1 | UI Test | Jayesh | 2021-01-21 | 2021-01-28 | 1 | 70%
4.2 | Data base Test | Jayesh,Yash | 2021-01-25 | 2021-01-31 | 1 | 70%
4.3 | Error Check | Tejas | 2021-02-01 | 2021-02-07 | 1 | 70%
4.4 | Objectives Testing | Tejas | 2021-02-08 | 2021-02-15 | 1 | 70%
5 | BlackBook
5.1 | Documentation | Tejas,Jayesh,Yash | 2021-02-16 | 2021-02-22 | 1 | 80%